## Sheet1
Months Out | Target Date | Task | Assigned Person | Complete | Actual Date
18-24 months |  | Site and host institutions defined |  | Y
|  | Tentative budget developed |  | Y
|  | Create and distribute event RFP |  | Y | 2010-02-15
18 months |  | Chair selected |  | Y
|  | Theme selected |  | Y
|  | Sign hotel contract |  | Y | 2010-02-15
12 months |  | Prepare and distribute decorator RFP | Prob won't do
|  | Prepare and distribute A/V RFP, if necessary | AV Comp from 2009
|  | Establish Program Committee structure | Pending
|  | Budget to Board for Approval |  | Y
|  | Post Call for Submissions to website, send blast email |  | Y
|  | Create Call for Submissions Postcard | Prob won't do
|  | Mail Call for Submissions Postcard | Prob won't do
10 months |  | Agree on Theme and Design |  | Y
|  | Draft Conference Schedule | Pending!!!
|  | Reccommendations for Keynote Speaker | Pending!!!
| 2010-04-04 | Open Call for Submissions
Update Exhibit Spondorship Database
| 2010-04-16 | Open Call for Reviewers
9 months |  | Implement timeline for Local Planning Committee | Pending!!!
| 2010-05-11 | Receive Abstract Reviewers Applications | Pending!!!
|  | Select and notify Abstract Reviewers | Pending!!!
|  | Create potential Exhibitors Mailing list | Done
|  | Compare decorator RFPs and make selection | Won't do
|  | Sign decorator contract | Done
|  | Prepare Call for Exhibits | Pending!!!
|  | Mail Call for Exhibits | Pending!!!
|  | Post Call for Exhibits to website | Pending!!!
VIP rooming list to hotel
8 months | 2010-06-03 | Call for Submissions closes | End of April
| 2010-06-04 | Abstracts to be automatically matched according to categories and distributed to reviers. | End of April
| 2010-06-04 | Send reviewers link to Submission Review area | Won't do
|  | Create Keynote invitations | Have to confirm
|  | Complete hotel credit application | Done
|  | Send RFP to printers for Preliminary and Onsite Brochures | Beginning of Sept
|  | Hotel Deposit due, if applicable | N/A
|  | Compare printer RFPs and make selection | Done
| 2010-06-20 | Reviewer Deadline | End of May
7 months |  | Creating Meeting Room Matrix | End of June
|  | Send first promotional email blast | Pending!!!
| 2010-07-16 | Proposed progam and abtract selections sent to Planning comminttee
Abstracts, posters, and symposia selected
Notify Staff of Abstract Selection
Review and confirm Budget compliance (menus, A/V, etc).
Confirm hotel shipping address
Create registration, exhibitor, and sponsor letters in database
Review hotel contract, begin assigining rooms, and review room block reduction deadline
Begin ordering labels for preliminary program
Request a linkto hotel reservation system to add to online form
| 2010-08-01 | Finalize the program
Conference Call with Program Chair and President
6 months | 2010-08-02 | Send acceptance and rejection letters
| 2010-08-02 | Send presenter instructions, date and time of presentation with acceptance letters
Finalize and sign A/V agreement
Approve Conference Schedule
Approve Pre or Post Conference Schedule
Update conference template with program sessions
Post Conference on website
Send in CEU course descriptions for approval
Send 2nd promotional email blast
Prepare "Save the Date" postcard
Maill "Save the Date" postcard
Set-up meeting in database
Finalize keynote speakers
Compile preliminary brochure
Send sponsorship invoices
Create speaker files
Create speaker spreadsheet
| 2010-08-16 | Call for Student Submissions Opens
5 months |  | Preliminary brochure to printer
Select moderators for breakout and general sessions
Update/Revise budget if needed
Reccomendations for next year's theme
Give speaker list to Tammy for bookstore, if applicable
| 2010-09-16 | Deadline to receive ads for preliminary program
Research registration bags
Obtain sponsorship for registration bags
Obtain sponsor's logos
Update website with information note previously available (hotel, sponsors, travel, bookstore, etc. )
Sent 3rd promotional email blast
Create online registratation form
4 months out | 2010-10-02 | Deadline for Student Submissions Close
Send 4th Promo email
A/V Spreadsheet to A/V company rep
Compile CE booklet - Look at online options
Mail Preliminary Program to all non-member Speakers
Exhibitor - Early bird deadline
| 2010-10-24 | Selection of Student Abstracts
3 months out |  | Compile Onsite Program text
Place order for registration bags
Create hotel rooming list
Send 5th Promo email - Hotel cut-off date
Get shuttle info from hotel
Deadline to receive speaker handouts
Request hotel room pick up list
Assign booth numbers
Review meeting room assignments
Booth Location Request Deadline
Create Conference evaluation
2 months out |  | Send out security RFP
Schedule pre-con meeting
Send 6th Promo email (deadlines, hotel infor, speaker updates, etc).
Create signs
Create menus
Confirm cancellation insurance
Create workshop speaker break/procedures schedule
Create exhibitor evaluation
Request hotel pick up list
Send email to recruit volunteers
Send Continuing Education book to printer or test online
Deadline to receive ads for the onsite program
Send exhibitors shipping address and quantity for inserts
Send sponsorship thank you letters
Send reminder email to those speakers who have not yet registered/hotel reservations
Finalize taping matrix, if applicable
Request hotel room pick up list
Deadline to receive inserts for registration bags
Contact 08 CVB for lure brochures to insert into reg bags
Finalize security contract and sign
Early bird discount registration deadline
Finalize Board Meetings arrangements
Finalize Travel for keynotes
1 month out |  | Double check all keynotes, students and speakers are registered for Meeting
Double check all Keynotes and Board have hotel reservations
Room monitors selected and assigned to all sessions
Courteousy call to keynote and funding panel
Informational letter to monitors, moderators, vollunteers
Make shipping arrangements as needed
Order easels for signs as needed
Make sure all sponsors are in database
Make sure all Exhibitors are paid and in database
Request hotel room pick up list - double check
|  | Create a list of reg inserts for membership | ask Joyce
Notify staff of shipping date/time (as applicable)
Email Blast #?
Verify all speakers, VIPS, staff, ect. have reservations at the hotel
Create taping form, if applicable
Send all handouts and additional materials to Printer
|  | Create overall evaluation | CEU provider
Hotel deadline to receive rooming list
Send Onsite Program to printer
Create staffing schedule
Exhibit Cancellation deadline
Extend hotel cut-off date (if possible)
Make copies of the Disclosure form and stuff in reg envelopes for those who have not responded
2 wks prior |  | Hotel cut-off date
Stuff expense forms in speaker reg envelopes for Keynotes
2 wks prior |  | Create any cancellation notices for attendees
2 wks prior |  | Give hotel final guarantees for food and beverage
Event
Post Event |  | Email exhibitor evaluation with thank you
Send thank you letters to speakers and honoraria checks
|  | Work with support staff to compile evaluations | CEU provider
|  | Submit all final reports due to accrediting agencies within 30 days after meeting | CEU Provider
|  | Send evaluation summaries to Board, Program Committee and Speakers | BOD